OGP Joint Working Group Meeting

Action Points

16.00-17.30 March 20th, 2014

Location: TASC, Castleriver House, 14-15 Parliament Street, Dublin 2

Civil Society Members Present: Ivan Cooper (The Wheel), Flora Fleischer (Open Knowledge Foundation Ireland), Nuala Haughey (TASC, Transparency International Ireland), Antoin Ò Lachtnain (Digital Rights Ireland), Denis Parfenov (Active Citizen and Open Knowledge Foundation Ireland)

Civil Service Members Present: Conor McCann (PER), William Beausang (PER), Claire Martinez(PER)

Administrator: Claire O’Keeffe

Apologies: Andrew Jackson (An Taisce), Anne Colgan, Donal Enright (Department of Environment, Community and Local Government), Evelyn O’Connor (PER)

A number of action points emerged from this meeting, the sixth gathering of the OGP Joint Working group, continuing the collaborative process of drafting Ireland’s first OGP National Action plan.

         It was agreed to work on collaboratively drafting DPER’s OGP Draft National Action Plan, which was circulated at the meeting and which has already been populated with 15 draft actions. (This is the third draft of a National Action Plan outline circulated by D/PER). CS undertook to incorporate suggested additions and changes and to deliver a working draft to DEPR (Claire Martinez) before the next JWG meeting (March 27th).

         It was agreed that CS members would merge the Civil Society Priorities Tabular DPER Response document (also circulated at the meeting) as well as the CS proposals regarding OGP Capacity Development and Local Government with DPER’s Draft National Action Plan document.

         D/PER said it would  help set up meetings (in week commencing 24th March if possible) with CS members and officials from the Department of Justice and the Department of the Environment, Community and Local Government.